## Slide 1: High-Level pDTG Introduction Plan
Policy
Regulatory
Supply Chain
Training Plan
Transition Plan
Monitoring
Committee
Q3 2021 Q4 2021 Q1 2022 on…
Complete
Ongoing
Pre-Q3 2021
pDTG inclusion in national guidelines
pDTG concept note approval
Tentative US FDA approval of Macleods pDTG product
Update supply chain ordering tools to include pDTG
Pipeline procurement planning
Quantification
Secure funding for national procurement
Initiate procurement
Training plan development
Develop high-level transition plan
Update M&E tools to include pDTG
Development of pDTG TWG (meet monthly), focus on pDTG in ART Sub-committee meetings (quarterly), and inclusion of pDTG highlights at key recurring policy and supply chain Ministry meetings
Issue MoH circular with key HIV guideline updates
Fast track in-country clearance and/or national drug regulatory approval
Develop enhanced monitoring guide, SOPs, job aids, IEC materials
pDTG training materials and reporting template
Conduct training with Implementing Partners
Conduct facility trainings
Develop detailed transition plan
Determine eligibility criteria (e.g., VL criteria) for phased implementation
International supply security monitoring
Uptake & transition monitoring
Conduct support supervision and/ or mentorship
pDTG in-country arrival and dissemination to select facilities
Quantify future needs and ongoing orders
Based on pDTG availability, transition patients once pDTG is in country in secured amounts
These timelines are illustrative for demonstration purposes. Please edit as per country context
Tentative US FDA approval of Viatris pDTG product
6
7
5
4
3
2
1

## Slide 2: Table 5: National Roll-Out High-Level Summary at Facility-Level for Patients
Public Sector
Private Sector (Optional)
National Targets
Phase I: July 2021
Phase II: September 2021
Initiate roll-out in XX high-volume sites distributed across the country
Initiate roll-out in XX private sector facilities across the country
70% of all eligible children initiated / transitioned onto pDTG-based regimens at phase I sites by December 2021
Introduce pDTG-based regimens at all remaining health facilities in a phased approach based on supply availability
Continue roll-out across all private sector facilities
All eligible existing and new patients initiated/ transitioned onto pDTG-based regimens by March 2022
These timelines are illustrative for demonstration purposes. Please edit as per country context

## Slide 3: Training summary with timelines
Month
March/ April
Activities
May/ June
July/ August
Develop training materials
Finalise training materials
During IP coordination meeting, introduce implementing partners (IPs) to HIV guideline updates via a high-level summary
Conduct X National Orientation Meetings (X-days each) to provide detailed updates on guideline changes; all IPs to be oriented
Disseminate guideline changes and pDTG transition plan to all key stakeholders including, political leaders, IPs, district health officers and civil society members
Meet directly with logisticians and IPs from selected public sector sites to prepare for pDTG ordering and facility-level stock management
Regional orientation meetings to be planned by IPs
Facility-level orientation to follow regional orientation; site trainings coordinated by IPs (ensure facility is oriented prior to receiving pDTG)
DTG-select sites to be prioritized for facility-level orientation
These timelines are illustrative for demonstration purposes. Please edit as per country context

## Slide 4: Community Engagement Plan
These timelines are illustrative for demonstration purposes. Please edit as per country context
Community Engagement Plan |  |  |  |  |  |  |  |  |  |  | 
Focal Activities | Q2 2021 |  |  | Q3 2021 |  |  | Q4 2021 |  |  | 2022 | 
 | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Finalisation of community workplan |  |  |  |  |  |  |  |  |  |  | 
Finalisation of pDTG patient literacy materials |  |  |  |  |  |  |  |  |  |  | 
Community sensitisation meeting |  |  |  |  |  |  |  |  |  |  | 
Community-level trainings |  |  |  |  |  |  |  |  |  |  |